## Instructions
How to Use this Template
1. Fill out the Project Title, Company Name, and Project Start Date.
2. Select the working calendar. This will adjust the Finish Dates and GANTT Chart based on the calendar chosen.
0 = 7 Days per Week
1 = 5 Days per Week
11 = Sundays Off
3. The Display Week changes the timeframe shown in the GANTT Chart.
4. Enter your Task Descriptions, Start Dates and Durations - the Finish Dates will be calculated. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting.
5. Start Dates are based on the Finish Date of the preceding activity (Finish to Start). These dates can be overwritten if required.
6. Progress can be tracked by typing the value into the Progress Column. I.E. 50 = 50%
7. The Data Date defaults to today's date. This can be overwritten.
8. Insert additional tasks by inserting new rows (if required).

## Project Schedule
PROJECT TITLE
Company Name
Project Start: | 2023-06-01
Display Week: | 1
Working Calendar: | 0
7 Days Per Week
[6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24
DATA DATE: | 2026-08-05 | time axis 2023-05-29 to 2023-07-30
TASK ID | TASK DESCRIPTION | PROGRESS | START DATE | END DATE | DURATION DAYS | time axis 2023-05-29 to 2023-07-30
WORK BREAKDOWN STRUCTURE - 1
1 | Task 1 | 90% | 2023-06-01 | 2023-06-08 | 8
2 | Task 2 | 30% | 2023-06-09 | 2023-06-10 | 2
3 | Task 3 | 30% | 2023-06-11 | 2023-06-12 | 2
4 | Task 4 | 5% | 2023-06-13 | 2023-06-14 | 2
5 | Task 5 | 5% | 2023-06-15 | 2023-06-16 | 2
WORK BREAKDOWN STRUCTURE - 2
6 | Task 6 |  | 2023-06-17 | 2023-06-18 | 2
7 | Task 7 |  | 2023-06-19 | 2023-06-20 | 2
8 | Task 8 |  | 2023-06-21 | 2023-06-22 | 2
9 | Task 9 |  | 2023-06-23 | 2023-06-24 | 2
10 | Task 10 |  | 2023-06-25 | 2023-06-26 | 2
WORK BREAKDOWN STRUCTURE - 3
11 | Task 11 |  | 2023-06-27 | 2023-06-28 | 2
12 | Task 12 |  | 2023-06-29 | 2023-06-30 | 2
13 | Task 13 |  | 2023-07-01 | 2023-07-02 | 2
14 | Task 14 |  | 2023-07-03 | 2023-07-04 | 2
15 | Task 15 |  | 2023-07-05 | 2023-07-06 | 2
WORK BREAKDOWN STRUCTURE - 4
16 | Task 16 |  | 2023-07-07 | 2023-07-08 | 2
17 | Task 17 |  | 2023-07-09 | 2023-07-10 | 2
18 | Task 18 |  | 2023-07-11 | 2023-07-12 | 2
19 | Task 19 |  | 2023-07-13 | 2023-07-14 | 2
20 | Task 20 |  | 2023-07-15 | 2023-07-16 | 2
WORK BREAKDOWN STRUCTURE - 5
21 | Task 21 |  | 2023-07-17 | 2023-07-18 | 2
22 | Task 22 |  | 2023-07-19 | 2023-07-20 | 2
23 | Task 23 |  | 2023-07-21 | 2023-07-22 | 2
24 | Task 24 |  | 2023-07-23 | 2023-07-24 | 2
25 | Task 25 |  | 2023-07-25 | 2023-07-26 | 2
To Add More Tasks Insert Rows Above This Line And Drag Down Page Break Line
|  |  | 0 | 1 | 11
Note on C5: 0 = 7 Days per Week 1 = 5 Days per Week 11 = Sundays Off
Note on F9: This date is calculated based on the Start Date + the Duration.